## Slide 1: MARDS, NEO Monitoring Visit #3
Overview by
Prof. dr Radovan Stojanovic
University of Montenegro

## Slide 2: Agenda
Overview of the Coordinator Prof. dr Radovan Stojanovic.
Overview of the Coordinating institution, Vladan Perazic
Partner UDG, report on activities
Partner “Privredna komora”, report on activities
Partner, bivše Ministarstvo nauke, report on activities
Partner, bivše Ministarstvo prosvjete, report on activities
The representative of the interested future students
Actual problems, COVID, operational and financial
NEO observations, recommendations and opinions
Discussion

## Slide 3: Instead introduction
General project progress and workflow is given and illustrated at:
https://www.mards.ucg.ac.me/workflow.html
Overview in this presentation is for period from June 2020 – Feb 2021
The level of the realized activities Marking
good
partially done
critical

## Slide 4: Content
Instead introduction?
Where we are?
Main problems and Mitigation ?
My and your our opinions?

## Slide 5: Where we are at M29?
By Activities. See Workflow
All activities by workflow are done
https://www.mards.ucg.ac.me//workflow.html#O37
By deliverables
See the work plan for all 3 years!!!
  In excel or in image
Done
Done
Partially done
In delay or critical

## Slide 6
We
are
here!

## Slide 7: Where we are by M29?
D2.1_A, Info on academic and professional training of WB staff/professionals/administrative' at EU“, Report, M18, UMB
D2.1,D2.2, D2.1 Report on academic and professional training of WB staff/professionals/administrative' at EU
D2.2 Guidelines and recommendations for WB academics and professionals in doctoral studies, Report, M24
D3.1, Report on appropriate funding doctoral studies in Montenegro and Albania,M22, Ministries in Albania and Montenegro,
D3.2D3.3, M28, Obligatory decision on adopting MARDS's methodology on funding for Montenegro and Albania, Misistries of Albania and Montenegro
Delay 7 Moths
Delay 7 Moths
Done
Done
Done

## Slide 8: Where we are by M29?
DE4.4 Final version of accreditation application Report, M18 "University Shkoder and University of Montenegro other Albanian Unis
D4.5: Decisions on Accreditation, M20, Ministries in Albania and Montenegro
D4.6: The list of the enrolled students, M24, Podgorica, Shkoder
D7.3: Doctoral Scholarships provided, M23 Metropolitan University Tirana (under help of UoM)
DE8.1 Overall project management All outputs "M1-M36 Every 3 months will be checked deliverables, M1-M36, UoM
D8.2 Project coordination meetings, M1-M36, UoM
DE8.3 Periodical report. MID TERM. M18, UoM
Delay 9 Moth!
Delay 6 Moths!
Done
Done
Done
Done
Podgorica, partially
Shkoder, no info

## Slide 9: Main problems and mitigation
D3.1, Report on appropriate funding, delay 6 months
  Ministries in Montenegro and in Albania with helps with Universities in Albania and Montenegro in next month to finish Reports, responsible Jelena Šaranović, Marko Vukasinovic, Montenegro, Ingrid Jushi (Albania)
D3.2D3.3, M28, Obligatory decision on adopting MARDS's methodology on funding for Montenegro and Albania, delay 7 months
  Senates/Upravni odbor of UoM and Ushkoder decision about free of fees for first generation of the students responsible (Predrag Miranovic, Arjeta Troshani) in next 3 months
D4.5: Decisions on Accreditation for Albania and Montenegro, delay 9 months
  Application submitted to AKOKVO in next 2 weeks and AKOKVO Taking decision in before May 2021. For Albania they should to have decision. Responsible Mladen Prazic, Radovan Stojanovic, Sanja Pekovic.
D7.3: Doctoral Scholarships provided, delay 6 months
  Till July 2021 do have decisions from Ministries Universities and other Institutions about Scholarships, Predrag Miranovic, Biljana Scepanovic, Rektor, Nedjeljko Latinovic
Problem
Mitigation

## Slide 10: Main problems and mitigation
Paying to partners
  Till end of the March 2021, Audit to finish job or to cancel agreement, Responsible, Vladan, Nikola, Vesna Rasovic
Paying to external experts
  Till June 2021, after approval of firs QR from Matjaz Debevc
Paying to others (translators, subcontracting etc)
  Radovan Stojanovic, Vesna Rasovic, Vladav Perazic
Subscription (upis) (translators, subcontracting etc)
  Predrag Miranovic and Nedjeljko Latinovic
  Helping Albanian partner
  Radovan Stojanovic, Arjeta, Betim
Problem
Mitigation

## Slide 11: Main problems and mitigation?
Management activities
  Radovan Stojanovic, Mladen Perazic, Ana Trninic
  Dissemination activities, saradnja sa privredom
  Nikolina Radulovic, Mladen Tanja, Sandra, Albanian side
Doctoral colloquium
  Biljana Scepanovic
Lessons and implementation for 1st year
  Centre for Doctoral Studies
Problem
Mitigation

## Slide 12: My opinion (recommendations)
Covid 19 problem partialy damaged project. University of Montenegro delayed activities, sometimes without any rationale reason. Albanian side do not follow EU agenda and Erasmus Rules.
Priorities of priorities
  Request for extension (rector, coordinator, int office), next 15 days
  Info about changing partners (rectors, coordinators, changed partners, int office), next 15 days
  Application for accreditation to to AKOKVO (Rector, Pekovic, Miranovic, administrator), next 15 days
  Info on subjects (as example names of the professors PMF, Miranovic), next 15 days
  Status of the further students in term of payments (scholarships) (Rector, Upravni odbor, Miranovic, Ministries), next 2 months
  Organization of the lesson process (Centre for doctoral studies), next 3 months
  Problem of Albanian Accreditation Remain and it is necessary to help them even by merginig-joining, (Stojanovic, Tinaj, Vladan, Betim, Arjeta), next 1 months
  Above follows R. Stojanovic and M. Perazic and local coordinators

## Slide 13: Yours opinions (recommendations)
Opinions?
Recommendations?
Discussion?
Maybe at the end of meeting?