## Slide 1
Conference and
Notes from Coordinator for NEO Monitoring visit :
Prof. dr Radovan Stojanovic

## Slide 2: What is our project?
Reforming doctoral studies in Montenegro and Albania – good practice paradigm (MARDS)
Capacity building
Specific measures
Curricula development
Specific measures output: improved PhD policy in 2 countries
Curricula development output: 2 Joint Doctoral Schools (Programs)

## Slide 3: Time-line and outputs
Policy improvement
proposed
O1: The proposal of
documents for
improvement submitted
O2: staff and professionals
trained
O3: equipment operative
Enrolment of the 1st gen
February 2021
Nov 19
Nov 20
Improved policy and Pilot Curricula
Running
Measures (scholarships etc)
issued
The lessons and research
are running
The lessons and research sustain
Pilot Joint Curricula
prepared
Curricula prepared
Curricula approved and accredited
Call for students announced
March 21
Dissemination, Quality Control, MAnagment

## Slide 4: Status of deliverables
O1: DE1.1 | In Progress: Middle of June will be on site | "Report on the “state of the art” in doctoral education in Montenegro and Albania and comparison with EU practices" Report M5 "University of Zagreb (University of Vienna)" | University of Vienna and University of Zagreb
O1: DE1.2 | In Progress: Middle of June will be on site | "Proceedings/Notes from conference about doctoral education in Western Balkan | University of Zagreb and University of Vienna
O1: D1.3 | On time: after September Will be submitted | Legal documents to be send to responsible bodies for adopting Report on funding doctoral studies in Montenegro and Albania | University of Montenegro, University of Shkoder
O2: DE2.X | Vienna ‘s training done Preparing Dubrovnik ‘s and Banska Bitrica’’s training | Training | University of Banska Bistrica
O3: DE4.3 | Tender prepared, waiting on document from Ministry | The report on Equipment | All
DE5.1 | Going according plan | Quality Plan | University of Maribor
DE6.1 and DE6.2 | Need more actions, especially | Dissemination Activities MARDS_A 6.2_Dissemination Plan_draft by Vienna | All
DE6.3 |  | Dissemination to stakeholders | All
DE7.1 |  | Sustainable strategy adopted | Metropolitan Uni, UniSHK and UoM
DE8.1, 8.2 |  | Project Managment | UoM

## Slide 5: Problems?
Slow coordination in term of equipment, weak
response of responsible bodies
Weak response of Ministries in improving policy
Weak response of non-academic partners

## Slide 6: Your questions
Thanks!