P7 UNIVERSITY OF Shkodra “Luigj Gurakuqi”

REPORT EQUIPMENT

According to the project application, UNISHK has prepared detail specification for equipment.  Detail specification include description of the item and purpose as well. Specification has been sent to the Agency EACEA for approval.

After approval received, tender procedure has been started. All documentation are available according to request:

- Revision of equipment and specification has been done

- Tendering documentation has been announced on portal of Public Procurement on 12.03.2020 and because COVID 19 situation it has been postponed on 04.05.2020.

- Based on the documents submitted, the Committee for the evaluation of received bids and selection of the best supplier for procurement of technical equipment for the realization choose the offer of the company “ONI shpk” on 06.05.2020.

- Agreement with “ONI shpk” signed on 03.06.2020.

- The payment of “ONI shpk” has been finalized on 03.07.2020 and all the invoices and equipment specifications has been sent to the MARDS project coordinator.

- One room was totally equipped with MARDS all-in-one computers.

All documentation regarding procurement of the equipment is available on the website of the University of Shkodra:

https://unishk.edu.al/kerkimi-shkencor/projekte/mards-project