## Slide 1: MARDS REFORMING DOCTORAL STUDIES IN MONTENEGRO AND ALBANIA – GOOD PRACTICE PARADIGM Grant: 598465-EPP-1-2018-1-ME-EPPKA2-CBHE-SP
February 2020 – September 2021 Overview by
Prof. dr Radovan Stojanovic
University of Montenegro

## Slide 2: Legend
Level of implementation
Done
Partially done or ongoing
Not done (need urgent action)

## Slide 3: General aims
Policy improvement in PhD education in Montenegro and Albania.
Improvement in practice by know-how show

## Slide 4: Why we are ?
Force majeure
Bureaucratic Inertia
Ambitious project
https://seeds.law/en/corona/corona-crisis-and-force-majeure/
https://www.linkedin.com/pulse/bureaucratic-inertia-aiding-abetting-terror-dr-steven-martello

## Slide 5: From WPs to deliverables
WPs
  Activities
    Deliverables
Shkoder’s Meeting, Oct, 2021

## Slide 6: WP1
WP1/PRE | Monitoring and analyzing of national systems and policies of doctoral education in Montenegro and Albania and comparing with EU practices
A1.1 | Evaluation of the existing doctoral education policy and standards in Montenegro and Albania and comparing with EU practices
A1.2 | Organization of a Conference on doctoral education in Montenegro and Albania
A1.3 | Recommendations and purpose of basic legal documents on university and national levels

## Slide 7: WP1-Deliverables
Delivarable # |  | Type | Month | Responsible | New Month
DE1.1 | Report on the “state of the art” in doctoral education in Montenegro and Albania and comparison with EU practices | Report | M5 | University of Zagreb (University of Vienna) | 
DE1.2 | Proceedings from conference about doctoral education in Montenegro and Albania | Report, Product | M7 | University of Zagreb (University of Vienna) | 
DE1.3 | Legal documents to be send to responsible bodies for adopting | Report | M12 | All | 

## Slide 8: WP2
WP2/DEV | Training of Montenegrin and Albanian academic staff and professionals/administration in doctoral education | 
A2.1 | Training of academic and professional staff on EU practices of doctoral education | University of Banska Bystrica (University of Vienna)
A2.2 | Creating a Guidelines and recommendations for WB academics and professionals in doctoral studies | University of Banska Bystrica (University of Vienna)

## Slide 9: WP2-Deliverables
DE2.1_A | Info on academic and professional training of WB staff/professionals/administrative' at EU | Report | M18 | University of Banska Bystrica (University of Vienna) | 
DE2.1_B | Report on academic and professional training of WB staff/professionals/administrative' at EU | Report | M24 | University of Banska Bystrica (University of Vienna) | 
DE2.2 | Guidelines and recommendations for WB academics and professionals in doctoral studies | Teaching and training material | M24 | University of Banska Bystrica (University of Vienna) | 

## Slide 10: WP3
WP3/DEV | Establishing a new model of funding doctoral studies on national levels. | 
A3.1 | Evaluation of models for funding doctoral studies in Montenegro and Albania | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences).
A3.2 | Adoption of bylaws on funding doctoral studies in Montenegro | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences).
A3.3 | Adoption of bylaws on funding doctoral studies in Albania | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences).

## Slide 11: WP3-Deliverables
DE3.1 | Report on appropriate funding doctoral studies in Montenegro and Albania | Report | M21 | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences). | JAN22
DE3.2 | Obligatory decision on adopting MARDS's methodology on funding for Montenegro | Decission | M28 | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences). | FEB22
DE3.2 | Obligatory decision on adopting MARDS's methodology on funding for Albania | Decission | M28 | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences). | FEB22

## Slide 12: WP4
WP4/DEV | Establishment and start-up of Joint Pilot Doctoral Schools
A4.1 | Development of the Curricula for joint Doctoral Schools
A4.2 | Equipping the laboratories and other infrastructure at partner universities
A4.3 | Accreditation of the Doctoral Schools
A4.4 | Enrolling the first generation

## Slide 13: WP4-Delievrables
DE4.1 | Curricula book for Joint School suited in Albania (Shkoder) | Teaching, Learning and Training material | M18 | Univershity Shkoder and University of Montenegro | 
DE4.2 | Curricula book for Joint pilot school in Montenegro | Teaching, Learning and Training material | M18 | Univershity Shkoder and University of Montenegro | 
DE4.3 | The report on MARDS’s equipment resources | Report | M12 | Univershity Shkoder and University of Montenegro other Albanian Unis | 
DE4.4 | Final version of accreditation application | Report | M18 | Univershity Shkoder and University of Montenegro other Albanian Unis | 
DE4.5A | Decisions on accreditation | Decission | M20 | Montenegro | 
D45.B | Decisions on accreditation | Decission | M20 | Albania | JAN22
DE4.6A | The list of enrolled students | List | M24 | Montenegro | OCT22
DE4.6B | The list of enrolled students | List | M24 | Albania | JAN22

## Slide 14: WP5
W5/QPLN | Quality plan | 
A5.1 | Internal Quality Control | University of Maribor (University of Vienna)
A5.2 | External Quality Control | University of Maribor (University of Vienna)

## Slide 15: WP5-Deliverables
DE5.1 | Quality Plan adopted | Report Service | M3 | University of Maribor University of Vienna | 
DE5.2 | Internal quality assurance reports delivered | Report | M36 | University of Maribor University of Vienna | 
DE5.3 | Tender for subtracting external QC experts completed | Service | M13 | University of Maribor University of Vienna | 
DE5.4 | External quality control and monitoring delivered | Report | M36 | External Experts | 
Shkoder’s Meeting, Oct, 2021

## Slide 16: WP6
WP6/DISS EXP | Dissemination of the project
A6.1 | Creation and updating project web site
A6.2 | Creating and distribution of dissemination documents
A6.3 | Organizing dissemination conference with stakeholders

## Slide 17: WP6-Deliverables
DE6.1 | Setting up and maintaining the project web site | Product | M1-M36 Every 6 months will be checked this deliverables | Metropolitan University Tirana (under help of University of Montenegro and PRIDE network) | 
DE6.2 | Dissemination material created and distributed | Product | M1-M36 Every 6 months will be checked this deliverables | Metropolitan University Tirana (under help of University of Montenegro and PRIDE network) | 
DE6.3 | Dissemination events with relevant stakeholders organised | Events | M6, M18, M24 | Metropolitan University Tirana (under help of University of Montenegro and PRIDE network) | 
DE6.4 | MARDS doctorial Colloquium organised | Event | M35 | Metropolitan University Tirana (under help of University of Montenegro and PRIDE network) | 

## Slide 18: WP7
WP7/DISS/EXP | Exploitation and Sustainability of the project results | 
A7.1 | Regular meetings about MARDS flow with stakeholders | Metropolitan University Tirana, Polytechnic Univerist of Tirana, Vlore Uni (under help of all)
A7.2 | Universities – stakeholders networking in Montenegro and Albania | Polytechnic University Tirana (under help of all)
A7.3 | Establishment of sustainable scholarships in Albania and Montenegro | 
A7.4 | Promotion of Doctoral School in Region | 

## Slide 19: WP7-Deliverables
DE7.1 | Sustainability strategy adopted | Document | M4 | Metropolitan University Tirana (under help of UoM) | 
DE7.2 | University – Stakeholders network created | Product Servise | M36 | Metropolitan University Tirana (under help of UoM) | 
DE7.3 | Doctoral scholarships provided | Product | M23 | Metropolitan University Tirana (under help of UoM) | 
Shkoder’s Meeting, Oct, 2021

## Slide 20: WP8
WP8/DISS/ EXP | Management of the project | 
A8.1 | Daily management of the project | University of Montenegro
A8.2 | Precise guidelines for management of the project | University of Montenegro
A8.3 | Regular meetings of project bodies | University of Montenegro

## Slide 21: WP8-Deliverables
DE8.1 | Overall project management | All outputs | M1-M36 Every 3 months will be checked this deliverables | University of Montenegro | 
DE8.2 | Project coordination meetings | Events | M1-M36 Deliverable valid for sheduled meetings | University of Montenegro | 
DE8.3 | Periodical and Final reports | Reports | M18, M36 | University of Montenegro | 
Shkoder’s Meeting, Oct, 2021

## Slide 22: 4th Year tasks?
D3.1 A: Report on appropriate funding doctoral studies in Montenegro, Responsible Ministry in Montenegro. Outcome: Report, done by Montenegrin Ministry with quantitative and qualitative analyses on funding doctoral studies, with emphasis on MARDS measures accepted by policy makers. Responsible, Montenegrin Ministry, Deadline JAN22.
D3.1 B Report on appropriate funding doctoral studies in Albania, Responsible Ministry in Albania. Outcome: Report, done by Albanian Ministry with quantitative and qualitative analyses on funding doctoral studies, with emphasis on MARDS measures accepted by policy makers. Responsible, Albanian Ministry, Deadline JAN22.
D3.2 The list of the measures on adopting MARDS' outcomes by relevant stakeholders in Montenegrin DE system. Montenegrin Team (UoM, UDG, Montenegrin Ministry, CEM) Outcome: Report, done by Montenegrin team with quantitative and qualitative analyses on adopting MARDS’ proposals and initiatives in reform DE in Montenegro. Set of accepted measures on institutional and national levels. Responsible UDG. Deadline FEB22.
D3.3 The list of the measures on adopting MARDS' outcomes by relevant stakeholders in Albanian DE system. (UNISHK, PUT, VLORE, UMT, MESY, UCCIAL) Albanian Ministry, CEM) Report, done by Albanian team with quantitative and qualitative analyses on adopting MARDS’ proposals and initiatives in reform DE in Albania. Set of accepted measures on institutional and national levels. Responsible UDG. Deadline FEB22.
D4.5 A: License Outcome in Montenegro: Licensed PhD programme in Montenegro. Deadline SEP21. Responsible Montenegrin Partners.
D4.5 B Solution for accreditation in Albania. Outcome: Licensed PhD programme in Albania. Deadline JAN22. Responsible. ALBANIAN PARTNERS.
D4.6 A: The list of the enrolled students, Podgorica Outcome: Lists of accepted PhD students in Montenegro. Deadline NOV21, Responsible UoM, UDG.

## Slide 23: 4th Year tasks?
8. D4.6 B: The list of the enrolled students, Skhoder, NOV21 Outcome: Lists of accepted PhD students in Albania. Deadline JAN21, Responsible UNISHK, UMT, UV, PUT
9. D5.3 Internal quality assurance reports delivered Outcome: Reports, Internal MID Report SEP21, Responsible UM and External Evaluators,
10. D5.4 External expert quality control and monitoring delivered. Outcome: External MID SEP21 and External FINAL, SEP22, Responsible UM and Coordinator of Internal Quality Control
11. D5.5 Feedback of the students and others included. Outcome: questionnaires, meetings… Responsible Prof. dr Nedjeljko Latinović
12. D6.4 MARDS doctorial Colloquium organized. Outcome: CFP, web page, review, presentations, Responsible Org Committee, Prof. dr Biljana Scepanovic
13. D6.5 Final Conference on MARDS project contribution in improving doctoral studies in Montenegro and Albania. Outcome: CFP, web page, review, presentations, Responsible Org Committee, Prof. dr Radovan Stojanovic
14. D7.2 A University – Stakeholders network in Albania created. Outcome: Dissemination activities, Contracts, Fairs…., Deadline up to the end of the project. All. Responsible UCCIAL and UMT, Collection UMT.
15. D7.2 B University – Stakeholders network in Montenegro created Outcome: Dissemination activities, Contracts, Fairs…., Deadline up to the end of the project. All. Responsible CEM, Collection UDG.
16. D7.3 Report on provided scholarships in Montenegro and Albania for DS, DEC 21. Outcome: Report on scholarships (PhD) in Montenegro and Albania, DEC21, Responsible, Montenegrin and Albanian teams.
17. D8.1 Overall project management All outputs, M1-M48. Every 3 months will be checked all deliverables
18. D8.2 Project coordination meetings and other meetings, M1-M48. Deliverable valid for scheduled meetings
19. D8.3 Periodical report, FINAL

## Slide 24: Conclusion
Not an easy job, which requires the efforts of all partners, cooperation and good management!