## YEAR 1-2 ACTIVITIES
|  |  | Agenda | Done | Partially | Critical | Up_ coming
WP, Actions, Deliverables | Titles | RESPONSIBLE PARTNER | INCLUDED PARTNER | nov18 | dec18 | jan19 | feb19 | mar19 | apr19 | may19 | jun19 | jul19 | aug19 | sep19 | okt19 | nov19 | dec19 | jan20 | feb20 | mart20 | apr20 | maj20 | jun20 | jul20 | aug20 | sep20 | okt 20 | nov20 | dec20 | jan21 | feb21 | mart 22 | apr21 | maj21 | jun21 | jul21 | aug21 | sep21 | okt21
WP1/PRE | Monitoring and analysing of national systems and policies of doctoral education in Montenegro and Albania and comparing with EU practices |  | ALL | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M4 | M35 | M36 | WP1
A1.1 | Evaluation of the existing doctoral education policy and standards in Montenegro and Albania and comparing with EU practices | University of Zagreb (University of Vienna) | ALL
A1.2 | Organization of a Conference on doctoral education in Montenegro and Albania | University of Zagreb (University of Vienna) | ALL
A1.3 | Recommendations and purpose of basic legal documents on university and national levels | University of Zagreb (University of Vienna) | ALL
Deliverables | [7 empty] | DEV1.1 |  | DEV1.2 |  |  |  |  | DEV1.3 | [24 empty] | WP1
WP2/DEV | Training of Montenegrin and Albanian academic staff and professionals/administration in doctoral education |  | ALL | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M4 | M35 | M36
A2.1 | Training of academic and professional staff on EU practices of doctoral education | University of Banska Bystrica (University of Vienna) | ALL
A2.2 | Creating a Guidelines and recommendations for WB academics and professionals in doctoral studies | University of Banska Bystrica (University of Vienna) | ALL
Deliverables | [20 empty] | D2.1_A | [5 empty] | D2.1 ,D2.2 | [12 empty] | WP2
WP3/DEV | Establishing a new model of funding doctoral studies on national levels. |  | ALL | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M4 | M35 | M36
A3.1 | Evaluation of models for funding doctoral studies in Montenegro and Albania | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences). | ALL
A3.2 | Adoption of bylaws on funding doctoral studies in Montenegro | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences). | ALL
A3.3 | Adoption of bylaws on funding doctoral studies in Albania | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences). | ALL
Deliverables | [24 empty] | D3.1 | [5 empty] | DE3.2 DE3.3 | [8 empty] | WP3
WP4/DEV | Establishment and start-up of Joint Pilot Doctoral Schools |  | ALL | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M4 | M35 | M36
A4.1 | Development of the Curricula for joint Doctoral Schools | University of Montenegro (University of Shkodra) | ALL
A4.2 | Equipping the laboratories and other infrastructure at partner universities | University of Montenegro (University of Shkodra) | ALL
A4.3 | Accreditation of the Doctoral Schools
A4.4 | Enrolling the first generation
Deliverables | [14 empty] | DEV4.3 | [5 empty] | D4.1 D4.2 D4.3 D4.4 |  | D4.5 |  |  |  | D4.6 | [12 empty] | WP4
W5/QPLN | Quality plan |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M4 | M35 | M36
A5.1 | Internal Quality Control | University of Maribor (University of Vienna) | ALL
A5.2 | External Quality Control | University of Maribor (University of Vienna) | ALL
Deliverables |  |  |  | M3: D5.1; DEV4.3 M13: D5.3; D4.6 M36: D5.2, D5.5 | WP5
WP6/DISS EXP | Dissemination of the project |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M4 | M35 | M36
A6.1 | Creation and updating project web site | University of Montenegro, UDG, under help of Metropolitan University Tirana and PRIDE network | ALL
A6.2 | Creating and distribution of dissemination documents | University of Montenegro, UDG, under help of Metropolitan University Tirana and PRIDE network | ALL
A6.3 | Organizing dissemination conference with stakeholders
Deliverables |  |  |  | D5.1 M6: D6.1 D6.2 D6.3; D5.1 M12: D6.1 D6.2 D.6.3; D5.3 M18: D6.1 D6.2 D6.3; D5.3 M35: D6.6; D5.2, D5.5 M36: DE6.4 | WP6
WP7/DISS/EXP | Explotation and Sustainability of the project results |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M4 | M35 | M36
A7.1 | Regular meetings about MARDS flow with stakeholders | Metropolitan University Tirana, Polytechnic Univerist of Tirana, Vlore Uni (under help of all) | ALL
A7.2 | Universities – stakeholders networking in Montenegro and Albania | Polytechnic University Tirana (under help of all) | ALL
A7.3 | Establishment of sustainable scholarships in Albania and Montenegro
A7.4 | Promotion of Doctoral School in Region
Deliverables |  |  |  | M4: D7.1; D6.1 D6.2 D6.3 M23: DE7.3; DE6.4 M36: DE7.2 | WP7
WP8/DISS/ EXP | Management of the project |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M4 | M35 | M36
A8.1 | Daily management of the project | University of Montenegro | ALL
A8.2 | Precise guidelines for management of the project | University of Montenegro | ALL
A8.3 | Regular meetings of project bodies | University of Montenegro | ALL
Deliverables |  |  |  | M3: D8.1; D7.1 M6: D8.1; D7.1 M9: D8.1; D7.1 M12: D8.1; D7.1 M15: D8.1; D7.1 M18: D8.1; D7.1 M21: D8.1; DE7.3 M24: D8.1; DE7.3 M27: D8.1; DE7.3 M30: D8.1
[5 empty] | D8.2 |  |  |  |  | D8.2 | [5 empty] | D8.2 |  |  |  |  | D8.3 |  |  |  |  | D8.2 |  |  |  |  | D8.2 |  |  |  |  | D8.2 |  |  | D8.3
|  |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M4 | M35 | M36 | WP1
Note on V1: Radovan: MID REPORT
Note on AG1: Radovan: WE ARE HERE
Note on X2: Radovan: 2nd NEO Montoring
Note on AG2: Radovan: 3 rd NEO Monitoring
Note on I7: Radovan Stojanovic: DE1.1 "Report on the “state of the art” in doctoral education in Montenegro and Albania and comparison with EU practices" Report M5 "University of Zagreb (University of Vienna)"
Note on K7: Radovan Stojanovic: DE1.2 "Proceedings from conference about doctoral education in Montenegro and Albania" "Report, Product" M7 "University of Zagreb (University of Vienna)"
Note on P7: Radovan Stojanovic: DE1.3 "Legal documents to be send to responsible bodies for adopting" Report M12
Note on V11: Radovan Stojanovic: DE2.1_A "Info on academic and professional training of WB staff/professionals/administrative' at EU" Report M18
Note on AB11: Radovan Stojanovic: D2.1 Report on academic and professional training of WB staff/professionals/administrative' at EU D2.2 Guidelines and recommendations for WB academics and professionals in doctoral studies
Note on Z16: Radovan Stojanovic: D3.1: Report on appropriate funding doctoral studies in Montenegro and Albania, Ministries in Albania and Montenegro
Note on AF16: Radovan: D3.2 D3.3 Obligatory decision on adopting MARDS's methodology on funding for Montenegro and Albania, Misistries of albania and montenegro
Note on P22: Radovan Stojanovic: DE4.3 The report on MARDS’s equipment resources Report M12 "Univershity Shkoder and University of Montenegro other Albanian Unis"
Note on V22: Radovan Stojanovic: DE4.1 Curricula book for Joint School suited in Albania (Shkoder) "Teaching, Learning and Training material" M18 "Univershity Shkoder and University of Montenegro" DE4.2 Curricula book for Joint pilot school in Montenegro "Teaching, Learning and Training material" , Univershity Shkoder and University of Montenegro" DE4.4 Final version of accreditation application Report, "Univershity Shkoder and University of Montenegro other Albanian Unis
Note on X22: Radovan Stojanovic: D4.5: Decisions on accreditation, Ministries in Albania and montenegro
Note on AB22: Radovan Stojanovic: D4.6: The list of the enroled studenst, Podgorica, Schoder
Note on G26: Radovan Stojanovic: DE5.1 Quality Plan adopted "Report Service", Maribor
Note on Q26: Radovan Stojanovic: DE5.3 Tender for subtracting external QC experts completed Service
Note on AN26: Radovan: D5.3: Internal quality assurance reports delivered, Maribor D5.4: E, eternal expertsternal quality control and monitoring delivered
Note on J31: Radovan Stojanovic: DE6.1 Setting up and maintaining the project web site Product "M1-M36 Every 6 months will be checked this deliverables" DE6.2 Dissemination material created and distributed Product "M1-M36 Every 6 months will be checked this deliverables" DE6.3 Dissemination events with relevant stakeholders organised Events M6, M18, M24 Metropolitan University Tirana (under help of University of Montenegro and PRIDE network)
Note on P31: Radovan Stojanovic: DE6.1 Setting up and maintaining the project web site Product "M1-M36 Every 6 months will be checked this deliverables" DE6.2 Dissemination material created and distributed Product "M1-M36 Every 6 months will be checked this deliverables" D6.2: Dissemination material created and distributed, Metropolitan D6.3: Dissemination events with relevant stakeholders organised, MU and pride
Note on V31: Radovan Stojanovic: DE6.1 Setting up and maintaining the project web site Product "M1-M36 Every 6 months will be checked this deliverables" DE6.2 Dissemination material created and distributed Product "M1-M36 Every 6 months will be checked this deliverables" DE6.3 Dissemination events with relevant stakeholders organised Events M6, M18, M24 Metropolitan University Tirana (under help of University of Montenegro and PRIDE network). DE6.2 Dissemination material created and distributed Product "M1-M36 Every 6 months will be checked this deliverables" D6.2: Dissemination material created and distributed, Metropolitan D6.3: Dissemination events with relevant stakeholders organised, MU and pride
Note on AM31: Radovan: D6.4: MARDS doctorial Colloquium organised, Metropolitan University Tirana (under help of University of Montenegro and PRIDE network)
Note on AN31: Radovan: D6.4: Metropolitan University Tirana (under help of University of Montenegro and PRIDE network)
Note on H37: Radovan Stojanovic: DE7.1 Sustainability strategy adopted Document M4
Note on AA37: Radovan: D7.3: Doctoral Scholarships providet, Metropolitan University Tirana (under help of UoM)
Note on AN37: Radovan: D7.2: University – Stakeholders network created, Metropolitan University Tirana (under help of UoM)
Note on G42: Radovan Stojanovic: DE8.1 Overall project management All outputs "M1-M36 Every 3 months will be checked this deliverables"
Note on J42: Radovan Stojanovic: DE8.1 Overall project management All outputs "M1-M36 Every 3 months will be checked this deliverables"
Note on M42: Radovan Stojanovic: DE8.1 Overall project management All outputs "M1-M36 Every 3 months will be checked this deliverables"
Note on P42: Radovan Stojanovic: DE8.1 Overall project management All outputs "M1-M36 Every 3 months will be checked this deliverables"
Note on S42: Radovan Stojanovic: DE8.1 Overall project management All outputs "M1-M36 Every 3 months will be checked this deliverables"
Note on V42: Radovan Stojanovic: DE8.1 Overall project management All outputs "M1-M36 Every 3 months will be checked this deliverables"
Note on Y42: Radovan Stojanovic: DE8.1 Overall project management All outputs "M1-M36 Every 3 months will be checked this deliverables"
Note on AB42: Radovan Stojanovic: DE8.1 Overall project management All outputs "M1-M36 Every 3 months will be checked this deliverables"
Note on AE42: Radovan Stojanovic: DE8.1 Overall project management All outputs "M1-M36 Every 3 months will be checked this deliverables"
Note on AH42: Radovan Stojanovic: DE8.1 Overall project management All outputs "M1-M36 Every 3 months will be checked this deliverables"
Note on F43: Radovan Stojanovic: DE8.2 Project coordination meetings Events "M1-M36 Deliverable valid for sheduled meetings"
Note on K43: Radovan Stojanovic: DE8.2 Project coordination meetings Events "M1-M36 Deliverable valid for sheduled meetings"
Note on Q43: Radovan Stojanovic: DE8.2 Project coordination meetings Events "M1-M36 Deliverable valid for sheduled meetings"
Note on V43: Radovan Stojanovic: DE8.3 Periodical report. MID TERM. Uom
Note on AA43: Radovan Stojanovic: DE8.2 Project coordination meetings Events "M1-M36 Deliverable valid for sheduled meetings"
Note on AF43: Radovan Stojanovic: DE8.2 Project coordination meetings Events "M1-M36 Deliverable valid for sheduled meetings"
Note on AK43: Radovan Stojanovic: DE8.2 Project coordination meetings Events "M1-M36 Deliverable valid for sheduled meetings"
Note on AN43: Radovan Stojanovic: DE8.3 Periodical report,FINAL

## DELIVERABLES
MARDS 's main delievrables (36) Months |  |  | blue: M25-M36 yellow: M18-M24
Delivarable # |  | Type | Month | Responsible | Expected Date
DE1.1 | Report on the “state of the art” in doctoral education in Montenegro and Albania and comparison with EU practices | Report | M5 | University of Zagreb (University of Vienna)
DE1.2 | Proceedings from conference about doctoral education in Montenegro and Albania | Report, Product | M7 | University of Zagreb (University of Vienna)
DE1.3 | Legal documents to be send to responsible bodies for adopting | Report | M12 | All
DE2.1_A | Info on academic and professional training of WB staff/professionals/administrative' at EU | Report | M18 | University of Banska Bystrica (University of Vienna)
DE2.1_B | Report on academic and professional training of WB staff/professionals/administrative' at EU | Report | M24 | University of Banska Bystrica (University of Vienna)
DE2.2 | Guidelines and recommendations for WB academics and professionals in doctoral studies | Teaching and training material | M24 | University of Banska Bystrica (University of Vienna)
DE3.1 | Report on appropriate funding doctoral studies in Montenegro and Albania | Report | M21 | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences).
DE3.2 | Obligatory decision on adopting MARDS's methodology on funding for Montenegro | Decission | M28 | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences).
DE3.2 | Obligatory decision on adopting MARDS's methodology on funding for Albania | Decission | M28 | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences).
DE4.1 | Curricula book for Joint School suited in Albania (Shkoder) | Teaching, Learning and Training material | M18 | Univershity Shkoder and University of Montenegro
DE4.2 | Curricula book for Joint pilot school in Montenegro | Teaching, Learning and Training material | M18 | Univershity Shkoder and University of Montenegro
DE4.3 | The report on MARDS’s equipment resources | Report | M12 | Univershity Shkoder and University of Montenegro other Albanian Unis
DE4.4 | Final version of accreditation application | Report | M18 | Univershity Shkoder and University of Montenegro other Albanian Unis
DE4.5 | Decisions on accreditation | Decission | M20 | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences).
DE4.6 | The list of enrolled students | List | M24 | University of Montenegro
DE5.1 | Quality Plan adopted | Report Service | M3 | University of Maribor University of Vienna
DE5.2 | Internal quality assurance reports delivered | Report | M36 | University of Maribor University of Vienna
DE5.3 | Tender for subtracting external QC experts completed | Service | M13 | University of Maribor University of Vienna
DE5.4 | External quality control and monitoring delivered | Report | M36 | External Experts
DE6.1 | Setting up and maintaining the project web site | Product | M1-M36 Every 6 months will be checked this deliverables | Metropolitan University Tirana (under help of University of Montenegro and PRIDE network)
DE6.2 | Dissemination material created and distributed | Product | M1-M36 Every 6 months will be checked this deliverables | Metropolitan University Tirana (under help of University of Montenegro and PRIDE network)
DE6.3 | Dissemination events with relevant stakeholders organised | Events | M6, M18, M24 | Metropolitan University Tirana (under help of University of Montenegro and PRIDE network)
DE6.4 | MARDS doctorial Colloquium organised | Event | M35 | Metropolitan University Tirana (under help of University of Montenegro and PRIDE network)
DE7.1 | Sustainability strategy adopted | Document | M4 | Metropolitan University Tirana (under help of UoM)
DE7.2 | University – Stakeholders network created | Product Servise | M36 | Metropolitan University Tirana (under help of UoM)
DE7.3 | Doctoral scholarships provided | Product | M23 | Metropolitan University Tirana (under help of UoM)
DE8.1 | Overall project management | All outputs | M1-M36 Every 3 months will be checked this deliverables | University of Montenegro
DE8.2 | Project coordination meetings | Events | M1-M36 Deliverable valid for sheduled meetings | University of Montenegro
DE8.3 | Periodical and Final reports | Reports | M18, M36 | University of Montenegro